Crewkerne Neighbourhood Plan

Project Plan

(Version 1.1)

Website: Crewkerneneighbourhoodplan.co.uk

November 2022

Crewkerne Neighbourhood Plan: Project Plan

| PROJECT PLAN SUMMARY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| STAGE | Sep | Oct | Nov | Dec | Jan 23 | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan 24 | Feb | Mar | Apr | May | Jun |
| 1. Getting Started | C1 | C1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2. Identify Issues |  | C2 | C2 | C2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3. Aims, Vision & Objectives |  |  |  |  | C3 | C3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4. Generate Options & Prepare Draft Plan |  |  |  |  |  |  |  |  |  | C4 | C5 | C5 |  | C6 | C6 | C6 |  |  |  |  |  |  |
| 5. Submission |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | S |  |  |  |
| 6. Post submission formal requirements |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Consultation windows:

C1 = Launch and initial awareness raising

C2 = Community questionnaire published

C3 = Community consultation (event / exhibition and publicity) on evidence feedback, emerging themes, draft vision, aims and objectives for comments and endorsement

C4 = Consult on development site options (if appropriate / necessary)

C5= Share first draft of plan with the community only to get comments and endorsement

C6 = Pre-submission consultation (including formal consultation with statutory consultees, but consult widely on content of plan)

S = Submission to local authority

Notes and Assumptions:

- The post submission stage is largely out of the hands of the NPSG and down to the local authority and appointed Examiner.  After submission, the process can take around 6 months to get the Plan made.

- The process may take a longer or shorter time depending on the matters dealt with in the Plan and the pace at which the NPSG can progress.

- Should site allocation not be required, a potential saving of 1 - 3 months can be made from stage 2.

| Stage 1 Getting Started: |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Task |  | Complete | Sep | Oct | Nov | Dec | Jan 23 | Feb |
| 1.1 | Designation of neighbourhood plan area |  |  |  |  |  |  |  |
| 1.2 | Initial launch and raising awareness (re-engagement) |  | C1 | C1 |  |  |  |  |
| 1.3 | Form NP steering group (NPSG) |  |  |  |  |  |  |  |
| 1.4 | NPSG Terms of reference drafted and approved |  |  |  |  |  |  |  |
| 1.5 | Budget/resources identified |  |  |  |  |  |  |  |
| 1.6 | Establish online presence and depository for activities, documents, etc |  |  |  |  |  |  |  |
| 1.7 | Initial project plan prepared |  |  |  |  |  |  |  |
| 1.8 | Initial project plan approved by NPSG (N.B. reviewed as necessary during process) |  |  |  |  |  |  |  |
| 1.9 | Project plan published online |  |  |  |  |  |  |  |
| 1.10 | Consultation and engagement plan prepared |  |  |  |  |  |  |  |
| 1.11 | Consultation and engagement plan approved by NPSG |  |  |  |  |  |  |  |
| 1.12 | Consultation and engagement plan published online |  |  |  |  |  |  |  |
| 1.13 | Identify local stakeholders (organisation, groups, clubs, etc.) |  |  |  |  |  |  |  |
| 1.14 | Identify strategic stakeholders (statutory consultees, wider-than-local organisations, service providers, interest groups and Agencies) |  |  |  |  |  |  |  |

| Stage 2 Identifying Issues: |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Task |  | Complete? | Aug | Sep | Oct | Nov | Dec | Jan 2023 | Feb | Mar | Apr | May |
| 2.1 | Understanding the existing strategic (wider than parish) written evidence base: reviewing evidence base and collating / summarising |  |  |  |  |  |  |  |  |  |  |  |
| 2.2 | Understanding the existing local written evidence base: reviewing evidence base and collating / summarising |  |  |  |  |  |  |  |  |  |  |  |
| 2.3 | Community views (questionnaire drafted) |  |  |  |  |  |  |  |  |  |  |  |
| 2.4 | Community views (questionnaire tested / pilot sample) |  |  |  |  |  |  |  |  |  |  |  |
| 2.5 | Community views (questionnaire published / distributed) |  |  |  | C2 | C2 |  |  |  |  |  |  |
| 2.6 | Questionnaire responses collated |  |  |  |  | C2 | C2 |  |  |  |  |  |
| 2.7 | Questionnaire responses analysed and report produced |  |  |  |  |  | C2 |  |  |  |  |  |
| 2.8 | Business views sought (if necessary) (interviews, questionnaire or focus groups) |  |  |  |  |  |  |  |  |  |  |  |
| 2.9 | Development potential exercise (if the allocation of housing, employment or other types of development is identified as an issue which needs pursuing through the neighbourhood plan): consider local call for sites and identify process; assess development potential & constraints * |  |  |  |  |  |  |  |  |  |  |  |
| 2.10 | Identify key issues, questions and gaps remaining and messages from above processes |  |  |  |  |  |  |  |  |  |  |  |
| 2.11 | Gaps in evidence: specialist studies (if necessary) |  |  |  |  |  |  |  |  |  |  |  |

* N.B.  Should site allocation not be required, a potential saving of 1 - 3 months can be made from stage 2 (ref. task 2.9).

| Stage 3 Aims, Vision & Objectives |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Task |  | Complete? | Dec | Jan 23 | Feb | Mar | Apr | May | Jun | Jul |
| 3.1 | Prepare draft aims and vision |  |  |  |  |  |  |  |  |  |
| 3.2 | Interpret draft aims and vision to prepare draft objectives (and seek informal input from local authority) |  |  |  |  |  |  |  |  |  |
| 3.3 | Consult on likely themes / topics of the plan, and the draft vision, aims & objectives and how they have been arrived at (i.e. start by telling the community what the issues and options stage told you about the key issues and messages). Seek comments and endorsement for the draft aims, vision and objectives, i.e. the thrust of the Plan. |  |  |  | C3 | C3 |  |  |  |  |
| 3.4 | Analyse comments and produce report of consultation |  |  |  |  |  |  |  |  |  |
| 3.5 | Approve vision, aims & objectives |  |  |  |  |  |  |  |  |  |

| Stage 4 Generate Options and Prepare Draft Plan |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Task |  | Complete? | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan 24 |
| 4.1 | Generate development options (if appropriate) |  |  |  |  |  |  |  |  |  |  |  |
| 4.2 | Additional ‘round’ of community consultation focused specifically on development options (if appropriate) |  |  |  | C4 |  |  |  |  |  |  |  |
| 4.3 | Analyse responses to options and finalise preferred option (if appropriate) |  |  |  |  |  |  |  |  |  |  |  |
| 4.4 | Draft NP Policy statements, maps and Plan text (including informal input from local authority) |  |  |  |  |  |  |  |  |  |  |  |
| 4.5 | Compliance: check compliances with national and local authority planning policy |  |  |  |  |  |  |  |  |  |  |  |
| 4.6 | Sustainability: contact local authority and request formal screening opinion on need or not for a Strategic Environmental Assessment and / or Habitat Regulations Assessment (likely to be required if proposing development in the neighbourhood plan or environment likely to be harmed as a result of the Plan’s policies.) N.B. The Local Authority has to allow statutory environmental agencies a 6 week period to give their view before responding formally. |  |  |  |  |  |  |  |  |  |  |  |
| 4.7 | Consultation document: share draft plan with community to get feedback and amend if necessary |  |  |  |  | C5 | C5 |  |  |  |  |  |
| 4.8 | Sustainability: strategic environmental assessment and / or habitats regulation assessment commissioned / undertaken and Plan amended if necessary |  |  |  |  |  |  |  |  |  |  |  |
| 4.9 | Approve draft plan |  |  |  |  |  |  |  |  |  |  |  |
| 4.10 | Pre-submission (Regulation 14) consultation: consult on pre-submission plan (includes formal consultation request to statutory consultees) |  |  |  |  |  |  |  | C6 | C6 | C6 |  |
| 4.11 | Sustainability: strategic environmental assessment and / or habitats regulation assessment refreshed if necessary |  |  |  |  |  |  |  |  |  |  |  |
| 4.12 | Amend Plan if necessary and document response to comments received |  |  |  |  |  |  |  |  |  |  |  |

| Stage 5 Submission |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Task |  | Complete? | Jan 24 | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct |
| 5.1 | Submission: Prepare required submission documents (e.g. statement of consultation, report of how the plan meets the ‘Basic Conditions’, SEA / HRA, Plan itself (as amended as a result of any changes brought about by pre-submission phase) |  |  |  |  |  |  |  |  |  |  |  |
| 5.2 | Submit plan and required documents to local authority |  |  |  | S |  |  |  |  |  |  |  |
| 5.3 | Post submission stage: out of the hands of the NPSG and down to the local authority and appointed Examiner. It can take around 6+ months to get to the point of getting the Plan ‘made’ (approved / adopted). |  |  |  |  |  |  |  |  |  |  |  |
| 5.4 | Independent Examiner appointed |  |  |  |  |  |  |  |  |  |  |  |
| 5.5 | Local authority legal compliance check |  |  |  |  |  |  |  |  |  |  |  |
| 5.6 | Regulation 16 consultation run by local authority |  |  |  |  |  |  |  |  |  |  |  |
| 5.7 | Examination |  |  |  |  |  |  |  |  |  |  |  |
| 5.8 | Examiner’s Report and final plan amendments |  |  |  |  |  |  |  |  |  |  |  |
| 5.9 | Referendum |  |  |  |  |  |  |  |  |  |  |  |